										00 70 50
Revised Dec. 2020									AMENDMENTS TO AGREEMENT
Project No.													       Page 1 of 1


										00 73 00
Revised Dec. 2020									SUPPLEMENTARY CONDITIONS
Project No.													       Page 1 of 1

June 2026											SUPPLEMENTARY CONDITIONS

Project No.													       Page 1 of 1

SPEC NOTE: These standard ‘Supplementary Conditions’ published by the Alberta Construction Association modify the General Conditions of CCDC 14 – 2026 Design-Build Stipulated Price Contract. They are intended for use only in the Province of Alberta, on projects to which the Alberta Prompt Payment and Construction Lien Act applies, to ensure compatibility of the contract with the Act.

1.1	INTENT

.1	These Supplementary Conditions amend the General Conditions forming part of CCDC 14 – 2026 as indicated. Provisions not amended remain in full force and effect.

1.2	AMENDMENTS TO GENERAL CONDITIONS

Delete GC 5.4.2, 5.4.3, 5.4.4, and 5.4.5 in their entirety and substitute:

5.4.2	The Payment Certifier will review the Work to verify the validity of the Design-Builder’s or a Subcontractor’s certificate of Substantial Performance of the Work and will promptly, and in any event, no later than 14 calendar days after receipt of the Design-Builder’s or a Subcontractor’s certificate of Substantial Performance of the Work: 
.1	advise the Design-Builder in writing that the Work or a Subcontractor’s portion of the Work is not substantially performed according to the requirements of the Payment Legislation and give reasons why, or
.2	verify in writing the certificate of Substantial Performance of the Work, with a copy to the Owner and the Design-Builder.
5.4.3	The Design-Builder shall, in accordance with GC 5.2 APPLICATIONS FOR PAYMENT, submit a proper invoice in accordance with the Payment Legislation for payment of all or part of the major lien fund: 
.1	no earlier than 46 days after issuance of a certificate of Substantial Performance of the Work, 
.2 	no earlier than 46 days after issuance of a certificate of Substantial Performance of the Work of a subcontract, and
.3	when the Owner is obligated to make a progressive release of lien holdback pursuant to the Payment Legislation.
5.4.4	The Owner shall, unless a statement of lien is registered, pay a proper invoice for payment of all or part of the major lien fund in accordance with the Payment Legislation.

Renumber GC 5.4.6, 5.4.7, and 5.4.8 as GC 5.4.5, 5.4.6, and 5.4.7 respectively.


END OF SECTION

